## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Student | Detecting human face | It will detect if the human face is present or not
|  | Student | Use best of algorithms | To detect human face accurately
|  | Student | Haar Cascading | Detects presence of human face
|  | Student | LBP (Local binary patterns) | Check if it is more proficient for face detection
1 | SB1/US2 | Student | Capturing Face | Capuring of face for feature extraction
1 | SB1/US3 | Student | Feature extraction for matching | Feature will be extracted for comparision
|  | Student | PCA using Eigen values | Data reduction
|  | Student | PCA using Fisher values | Data reduction
|  | Student | KNN | Data reduction
|  | Student | K-means | Data reduction
|  | Student | Haar-cascading | Data reduction
|  | Student | Wavelet Transformation | Data reduction
|  | Student | LBP (Local binary patterns) | Data reduction
|  | Student | Attribute Selection using Eigen values | Data reduction
|  | Student | Attribute Selection using Fisher values | Data reduction
1 | SB1/US4 | Student | Recognition of the face ( by recognizing use of eyes, nose ,eye location etc. ) | Recognizing face from dataset
|  | Student | Capturing all the faces | Capture of face
|  | Student | Recognition of the faces | Recognizing multiple faces
|  | Student | PCA using Eigen values | Extraction of data
|  | Student | PCA using Fisher values | Extraction of data
|  | Student | K-means | Extraction of data
|  | Student | Haar-cascading | Extraction of data
|  | Student | Wavelet Transformation | Extraction of data
|  | Student | LBP (Local binary patterns) | Extraction of data
|  | Student | Attribute Selection using Eigen values | Extraction of data
|  | Student | Attribute Selection using Fisher values | Extraction of data
1 | SB1/US5 | Student | Making it robust by time | Calculating time
|  | Student | Detecting multiple human faces | Multiple faces needed to be reconized in one frame
|  | Student | Creating dataset of faces for attendence(database) | So that only those faces will be marked who is present
|  | Student | Identifying and matching captured images from database | It will compare faces
|  | Student | Capturing videos | Video is capture for few minutes
|  | Student | Video meta data extraction | Capturing images from video with time frame
|  | Student | Fast and robust extraction key methods | Capturing frames with good exposure and light
|  | Student | Extracting clear image/face from the video | It will extract clear faces from the video to match with data sets
|  | Student | Matching extracted images from the dataset(using same algos mentioned above) | Match those images
|  | Student | Giving unique id to all the members of dataset | It will be displayed who is present in the class
|  | Student | Displaying of Ids when face from video is matched with dataset | Display of Id and its corresponding infos like name, roll no.
|  | Student | Making of attendence sheet with data base | Where record of present student will be displayed
|  | Student | Work Space | To store face/videos for matching
|  | Student | Desing GUI of the sheet | Designing of sheet
|  | Student | Making class wise databases | For attendence of each section
|  | Student | Connecting GUI with database | conectivity of database with camera
|  | Student | Connecting Video extraction | Output- attendence sheet is ready
|  | Student | List of all subjects | to see attendence of indivisual subjects
|  | Student | Login for indivisual subject attendence | to see result of attendence indivisually
|  | Student | Showing output on database | All attendence is counted in total
|  | Student | Marking of attendence | All attendence is counted in total
|  | Student | Implementation on the hardware | Practical Implimentation
|  | Student | conecting with the camera | Practical Implimentation
|  | Student | Implementing in the college | Real time applicaton implimentation
|  | Student | Track the accuracy and working | Testing on implimented application
|  | Student | Finding issues | Finding problem after implimentation
|  | Student | Resolving issues | Resolving the issue of the found problem
|  | Student | Impleting again | Finally impliment the system

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <AUTOMATIC FACE DETECTION>
SB1/US1 |  | SB1/D1/T1 | Detecting human face | HC + GK + RK
|  | SB1/D1/T2 | Use best of algorithms | HC + GK + RK
|  | SB1/D1/T3 | Haar Cascading | HC + GK + RK
|  | SB1/D1/T4 | LBP (Local binary patterns) | HC + GK + RK
|  | SB1/D1/T5 | Capturing Face | HC + GK + RK
|  | SB1/D1/T6 | Feature extraction for matching | HC + GK + RK
SB1/US2 |  | SB1/D2/T1 | PCA using Eigen values | HC + GK + RK
|  | SB1/D2/T2 | PCA using Fisher values | HC + GK + RK
|  | SB1/D2/T3 | KNN | HC + GK + RK
|  | SB1/D2/T4 | K-means | HC + GK + RK
|  | SB1/D2/T5 | Haar-cascading | HC + GK + RK
SB1/US3 |  | SB1/D3/T1 | Wavelet Transformation | HC + GK + RK
|  | SB1/D3/T2 | LBP (Local binary patterns) | HC + GK + RK
|  | SB1/D3/T3 | Attribute Selection using Eigen values | HC + GK + RK
|  | SB1/D3/T4 | Attribute Selection using Fisher values | HC + GK + RK
SB1/US6 |  | SB1/D4/T1 | Recognition of the face ( by recognizing use of eyes, nose ,eye location etc. ) | HC + GK + RK
|  | SB1/D4/T2 | Capturing all the faces | HC + GK + RK
|  | SB1/D4/T3 | Recognition of the faces | HC + GK + RK
|  | SB1/D4/T4 | PCA using Eigen values | HC + GK + RK
|  | SB1/D4/T5 | PCA using Fisher values | HC + GK + RK
SB1/US7 |  | SB1/D5/T1 | K-means | HC + GK + RK
|  | SB1/D5/T2 | Haar-cascading | HC + GK + RK
|  | SB1/D5/T3 | Wavelet Transformation | HC + GK + RK
|  | SB1/D5/T4 | LBP (Local binary patterns) | HC + GK + RK
SB1/US27 |  | SB1/D6/T1 | Attribute Selection using Eigen values | HC + GK + RK
|  | SB1/D6/T2 | Attribute Selection using Fisher values | HC + GK + RK
|  | SB1/D6/T3 | Making it robust by time | HC + GK + RK
|  | SB1/D6/T4 | Detecting multiple human faces | HC + GK + RK
SB1/D6/T5
SB1/US27 |  | SB1/D7/T2
SB1/D7/T3
SB1/D7/T4
SB1/D7/T5
SB1/US150 |  | SB1/D8/T1
SB1/D8/T2
SB1/D8/T3
SB1/D8/T4
SB1/US28 |  | SB1/D9/T1
SB1/D9/T2
SB1/D9/T3
SB1/D9/T4
SB1/D9/T5
SB1/US50 |  | SB1/D10/T1
SB1/D10/T2
SB1/D10/T3
SB1/D10/T4
SB1/D10/T5
SB1/US53 |  | SB1/D11/T2
SB1/D11/T3
SB1/D11/T4
SB1/D11/T5
SB1/US55 |  | SB1/D12/T1
SB1/D12/T2
SB1/D12/T3
SB1/D12/T4
SB1/US51 |  | SB1/D13/T1
SB1/D13/T2
SB1/D13/T3
SB1/D13/T4
SB1/D13/T5
SB1/US70 |  | SB1/D14/T1
SB1/D14/T2
SB1/D14/T3
SB1/D14/T4
SB1/D14/T5
SB1/US71 |  | SB1/D15/T2
SB1/D15/T3
SB1/D15/T4
SB1/D15/T5
SB1/US72 |  | SB1/D16/T1
SB1/D16/T2
SB1/D16/T3
SB1/D16/T4

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 20 | 20 | Tasks
2018-09-12 | 10 | 20
2018-09-11 | 7 | 20
2018-09-14 | 5 | 20
2018-09-16 | 5 | 20
2018-09-18 | 4 | 20
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <AUTOMATIC FACE DETECTION>
|  | SB2/D1/T1 | Creating dataset of faces for attendence(database) | GK + RK
|  | SB2/D1/T2 | Identifying and matching captured images from database | HC + GK + RK
|  | SB2/D1/T3 | Capturing videos | HC + GK + RK
|  | SB2/D2/T1 | Video meta data extraction | HC + GK + RK
|  | SB2/D2/T2 | Fast and robust extraction key methods | HC + GK + RK
|  | SB2/D2/T3 | Extracting clear image/face from the video | HC + GK + RK
|  | SB2/D2/T4 | Matching extracted images from the dataset(using same algos mentioned above) | HC + GK + RK
|  | SB2/D2/T5 | Giving unique id to all the members of dataset | HC + GK + RK
|  | SB2/D3/T1 | Displaying of Ids when face from video is matched with dataset | HC + GK + RK
SB2/D3/T2
SB2/D3/T3
SB2/D3/T4
SB2/D4/T1
SB2/D4/T2
SB2/D4/T3
SB2/D4/T4
SB2/D4/T5
SB2/D5/T1
SB2/D5/T2
SB2/D5/T3
SB2/D5/T4
SB2/D6/T1
SB2/D6/T2
SB2/D6/T3
SB2/D6/T4
SB2/D6/T5
SB2/D7/T1
SB2/D7/T2
SB2/D7/T3
SB2/D7/T4
SB2/D7/T5
SB2/D8/T1
SB2/D8/T2
SB2/D8/T3
SB2/D8/T4

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 15 | 15 | Tasks
2017-09-28 | 9 | 15
2017-10-02 | 5 | 15
2017-10-05 | 3 | 15
2017-10-07 | 4 | 15
2017-10-09 | 2 | 15
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <AUTOMATIC FACE DETECTION>
|  |  | Making of attendence sheet with data base | GK
|  |  | Work Space | GK
|  |  | Desing GUI of the sheet | HC + GK
|  |  | Making class wise databases | HC + GK
|  |  | Connecting GUI with database | GK
|  |  | Connecting Video extraction | HC + RK
|  |  | List of all subjects | HC
|  |  | Login for indivisual subject attendence | HC + GK
|  |  | Showing output on database | HC + GK
|  |  | Marking of attendence | HC+GK

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <AUTOMATIC FACE DETECTION>
|  |  | Implementation on the hardware | GK + RK
|  |  | conecting with the camera | GK + RK
|  |  | Implementing in the college | GK+ RK
|  |  | Track the accuracy and working | HC + GK + RK
|  |  | Finding issues | GK + RK
|  |  | Resolving issues | GK + RK
|  |  | Impleting again | GK + RK

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days